## Slide 1: Co Pilot driver statistics project
11/18/2016
Team members:
Vladimir Djukanovic
Leslie Dahlberg
Léa Brunschwig
Eric Engtorp
Fredrik Frenning
Pooria Ghavamian
Hamza Sabljakovic

## Slide 2: Trello – last week

## Slide 3: Last week - establishments
Project plan presentation (Wednesday at 21:00)
Most of the web portal implementation:
  Database
    Create database schema
    Insert dummy data
  GUI
    Add radial graph to the web portal
    Finish GUI implementation
  Functionality
    Connection with database
    Get top 20 high scores from database
    Connect GUI with data retrieved from database
  Refactor
  Web hosting service
Android application:
  Create algorithm for score and determine what data to measure and store
  Create activity for high score
  Set up SQL lite
  Create activities for time selection

## Slide 4: Web portal solution

## Slide 5: Select machine and alias screen

## Slide 6: Select time and game screen

## Slide 7: Scores – historic data

## Slide 8: Trello – following week

## Slide 9: Plan for following week
Implementation:
  Web Portal implementation:
    Switch between graphs (fuel, speed etc...)
    Refactor when finish
    Show high scores based on selected vehicle
  Android application implementation:
    Initial navigation and basic activities Android (Swiping, highscore, game, selecting machines, etc.) without detailed implementation of individual activities
    Create upload highscore function for Android
    Create GUI for main game screen
    Create activities for machine selection and alias selection
    Retouch of GUI for app
    Navigation between activities
    Upload high score function for Android
    Publish results dialog
Design description – preliminary document
  Short description - Lea
  High-level description - Eric
  Software architecture - Hamza
  Detailed software design - Leslie
  Graphical User Interface - Vladimir
  Concerns - Fredrik
  Review - Pooria

## Slide 10: Obstacles
Co Pilot responsiveness
Different GUI in compare with standard Android

## Slide 11: Worked hours
Name | Last week | Total
Vladimir Djukanovic | 27 | 57
Hamza Sabljakovic | 27 | 57
Léa Brunschwig | 0 (L) | 30
Eric Engtorp | 20 | 55
Fredrik Frenning | 20 | 55
Pooria Ghavamian | 20 | 55
Leslie Dahlberg | 20 | 55
Legend: L = on leave (approved by the group)